## Task Tracker
Task Name | Description | Assigned Team Member | Start Date | Due Date | Priority | Status | Progress (%)
Task 1 | Design the homepage | Alice | 2024-06-01 | 2024-06-10 | High | In Progress | 50%
Task 6 | Create marketing strategy | Frank | 2024-06-03 | 2024-06-12 | Medium | In Progress | 40%
Task 8 | Perform code review | Heidi | 2024-06-04 | 2024-06-13 | Low | Completed | 100%
Task 2 | Develop backend API | Bob | 2024-06-02 | 2024-06-15 | Medium | Not Started | 0%
Task 9 | Conduct user testing | Ivan | 2024-06-07 | 2024-06-17 | High | In Progress | 60%
Task 4 | Test the application | Dave | 2024-06-08 | 2024-06-18 | High | Not Started | 0%
Task 10 | Optimize database | Judy | 2024-06-09 | 2024-06-19 | Medium | Not Started | 0%
Task 3 | Write documentation | Charlie | 2024-06-05 | 2024-06-20 | Low | In Progress | 30%
Task 7 | Prepare user training | Grace | 2024-06-06 | 2024-06-22 | Medium | Not Started | 0%
Task 5 | Launch the product | Eve | 2024-06-10 | 2024-06-25 | High | Not Started | 0%

## Summary Metrics
Metric | Value
Total number of tasks | 10
Number of completed tasks | 1
Number of tasks in progress | 4
Number of overdue tasks | 0
Percentage of tasks completed | 0.1

## Summary Report
Priority | All
Sum of Progress (%) | Column Labels
Row Labels | Completed | In Progress | Not Started | Grand Total
Task 1 |  | 0.5 |  | 0.5
Task 10 |  |  | 0 | 0
Task 2 |  |  | 0 | 0
Task 3 |  | 0.3 |  | 0.3
Task 4 |  |  | 0 | 0
Task 5 |  |  | 0 | 0
Task 6 |  | 0.4 |  | 0.4
Task 7 |  |  | 0 | 0
Task 8 | 1 |  |  | 1
Task 9 |  | 0.6 |  | 0.6
Grand Total | 1 | 1.8 | 0 | 2.8

## Communication
Task Name | Update/Comment | Date | Team Member
Task 1 | Initial homepage design draft completed | 2024-06-02 | Alice
Task 2 | Backend API development started | 2024-06-05 | Bob
Task 3 | First draft of documentation ready | 2024-06-06 | Charlie
Task 4 | Test cases prepared for review | 2024-06-09 | Dave
Task 5 | Product launch strategy finalized | 2024-06-11 | Eve
Task 6 | Marketing strategy meeting scheduled | 2024-06-04 | Frank
Task 7 | Training material outline completed | 2024-06-08 | Grace
Task 8 | Code review feedback implemented | 2024-06-05 | Heidi
Task 9 | User testing phase started | 2024-06-07 | Ivan
Task 10 | Database optimization plan drafted | 2024-06-10 | Judy